## Defect Tracking Log
DEFECT TRACKING LOG
Project Name |  | https://www.nix.ba
Program Manager
Project Manager
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause
1 | 04.01.2026. | Edin Šehović | Description: During user registration, the input fields “Username”, “First Name”, and “Last Name” allow the entry of numbers and special characters. These fields should accept alphabetical characters only, as numeric and special characters are not valid for personal names or usernames. Expected Result: The system should restrict input in these fields to valid characters only (letters, and optionally allowed symbols such as hyphen or space). Actual Result: The system allows numbers and special characters without displaying any validation error. |  | Testing | Medium |  |  |  | New
2 | 04.01.2026. | Edin Šehović | Description: The “Date of Birth” field on the Registration form only validates whether the entered date is not in the future, but does not enforce a minimum age requirement (e.g. user must be at least 18 years old). Expected Result: The system should validate that the user meets the minimum age requirement (e.g. 18+ years). Actual Result: Users younger than the required age can successfully register. |  | Testing | Medium |  |  |  | New
3 | 04.01.2026. | Edin Šehović | Description: Input fields in the Contact form allow users to enter random or meaningless characters (e.g. symbols or mixed character strings) without validation. Expected Result: The system should validate input and prevent saving meaningless or invalid character combinations. Actual Result: The form accepts and saves invalid input values without any warnings. |  | Testing | Low |  |  |  | New
4 | 05.01.2026. | Azemina Magrdžija | Description: The “Phone Number” field allows the entry of alphabetical characters, which results in invalid phone number data being saved. Expected Result: The field should allow numeric input only (and optionally “+” for country code). Actual Result: Letters can be entered and saved without validation. |  | Testing | Medium |  |  |  | New
5 | 05.01.2026. | Almer Hodžić | Description: On the “New Product” form, mandatory fields are not marked with an asterisk (*), making it unclear to the user which fields must be filled in before submission. Expected Result: All required fields should be clearly marked with an asterisk (*). Actual Result: Users do not receive visual indication of mandatory fields. |  | Testing | Low |  |  |  | New
6 | 06.01.2026. | Almer Hodžić | Description: The “Price” field on the New Product form allows the entry of negative numeric values, which is not valid for product pricing. Expected Result: The system should prevent entering or saving negative price values. Actual Result: Negative numbers can be entered into the Price field. |  | Testing | High |  |  |  | New
7 | 06.01.2026. | Almer Hodžić | Description: The “Price” field allows the entry of the minus character (“-”), even though the form cannot be saved when this value is present. Expected Result: Invalid characters should be blocked at input level. Actual Result: The user can enter invalid characters, but saving fails without clear guidance. |  | Testing | Low |  |  |  | New
8 | 06.01.2026. | Azemina Magrdžija | Description: The system allows publishing a product without uploading an image, automatically assigning a placeholder image without notifying the user. Expected Result: The system should require an image upload or clearly warn the user before publishing. Actual Result: Products are published with a placeholder image without any warning. |  | Testing | Medium |  |  |  | New
9 | 06.01.2026. | Azemina Magrdžija | Description: In My Profile → Edit Profile, the Contact Details form allows saving invalid data, such as text values in the Postal Code and Phone Number fields. Expected Result: The system should validate numeric fields and prevent saving invalid data. Actual Result: Invalid data is saved successfully. |  | Testing | High |  |  |  | New
10 | 06.01.2026. | Azemina Magrdžija | Description: The chat system does not provide an option to delete sent messages or images, causing all content to remain permanently visible. Expected Result: Users should be able to delete their sent messages or media. Actual Result: There is no delete functionality available. |  | Testing | Medium |  |  |  | New

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).